## Task Tracker
PSUT LLM Engine - Phase 2 Project Task Breakdown
# | Task | Description | Est. Acc Days | Assignee
Milestone 1 - Requirements & Foundation · Weeks 1-6
1.1 | Kick-off meeting and project charter | Conduct internal kick-off with full team, define delivery scope, assign responsibilities, agree on communication cadence and sprint structure | 4 | Yazan Abu Osbeh
1.2 | Stakeholder requirements gathering - eLearning department | Meet with PSUT eLearning team to understand LMS structure, document management workflows, material publishing process, and API availability for integration | 6 | Yazan Abu Osbeh
1.3 | Stakeholder requirements gathering - student portal IT | Meet with PSUT portal IT team to understand portal architecture, available API endpoints, survey data structure, and report delivery and display requirements | 4 | Yazan Abu Osbeh
1.4 | Stakeholder requirements gathering - student registration | Meet with PSUT registration department to understand academic record data structure, data access method options, and semester data delivery process | 4 | Yazan Abu Osbeh
1.5 | Stakeholder requirements gathering - academic governance | Meet with PSUT academic governance team to understand compliance requirements, data privacy constraints, and report approval and sign-off process | 4 | Yazan Abu Osbeh
1.6 | Requirements consolidation and sign-off | Consolidate all stakeholder inputs into a unified requirements document, circulate for review, and obtain written sign-off from PSUT before development begins | 4 | Yazan Abu Osbeh
1.7 | Sprint planning and milestone scheduling | Break Phase 2 scope into sprints, assign tasks to team members, define milestone acceptance criteria, and set up internal progress tracking | 4 | Yazan Abu Osbeh
1.8 | System architecture design | Design full technical architecture for both subsystems , data flows, service boundaries, integration points, API contracts, infrastructure topology | 8 | Mahmoud Qaddoura
1.9 | Architecture review and sign-off | Review architecture design with team leads, incorporate feedback, and obtain internal sign-off before development begins | 4 | Mahmoud Qaddoura
1.10 | Database schema design | Design full PostgreSQL schema , users, courses, enrolments, chat sessions, messages, documents, document chunks, audit logs, report jobs, academic reports | 6 | Mahmoud Qaddoura
1.11 | Database schema peer review | Peer review schema design with fullstack engineer, finalise table relationships, confirm JSONB usage for report storage, validate indexing strategy | 4 | Mohammad Abzakh
1.12 | FastAPI project scaffold and repository setup | Initialise fresh repository, set up project directory structure , api, services, repositories, models, schemas, clients, utils, core , and configure linting and type checking | 4 | Mohammad Abzakh
1.13 | Core configuration and environment management | Implement Pydantic Settings class, define .env structure, document all required environment variables with descriptions and defaults | 2 | Mohammad Al Balawi
1.14 | Docker and Docker Compose setup | Write Dockerfile for application image, docker-compose for PostgreSQL and Qdrant services, configure volume mounts, networking, and health checks | 6 | Mohammad Al Balawi
1.15 | CI/CD pipeline setup | Configure GitHub Actions workflow with lint, type check, test, build, and deploy stages. Integrate Ruff for linting and Mypy for type checking | 6 | Lina Khalil
1.16 | Alembic migration setup | Initialise Alembic, configure async engine connection, write initial migration from approved schema design, verify migration on fresh database | 4 | Mohammad Abzakh
1.17 | SQLAlchemy ORM models | Implement all ORM models mapped to approved schema , User, Course, Section, Enrolment, ChatSession, ChatMessage, Document, DocumentChunk, AuditAI, ReportJob, AcademicReport | 8 | Abed Al Qader Madi
1.18 | Base repository pattern | Implement abstract base repository with generic CRUD operations, async session dependency injection, and standardised error handling | 6 | Abed Al Qader Madi
1.19 | JWT authentication foundation | Implement JWT token generation and validation, password hashing with bcrypt, auth middleware, token refresh logic, and protected route dependency | 8 | Yehya Mujahid
1.20 | Role-based access control | Implement role enum , student, lecturer, admin , dependency guards per role, course-scoped enrolment checks, and unauthorised access error handling | 6 | Yehya Mujahid
1.21 | Qdrant setup and per-semester collection strategy | Deploy Qdrant instance, define per-semester collection naming convention, implement collection creation and management utilities, test upsert and similarity query | 6 | Mahmoud Qaddoura
1.22 | Documentation - system architecture | Write system architecture document covering subsystem overview, component diagram, data flow diagrams, integration points, and infrastructure topology. To be completed after architecture sign-off. | 6 | Mahmoud Qaddoura
1.23 | Documentation - development environment setup guide | Write developer onboarding and environment setup guide covering repository structure, local environment setup, Docker usage, environment variables, and running the application locally. | 4 | Mohammad Abzakh
Estimated Effort in Accumulated Work Days: 124 ¦ Total Business days: 30
Milestone 2 - AI Tutor Core · Weeks 6-16
2.1 | PSUT LMS API client | Implement async HTTP client wrapping PSUT LMS API , authentication headers, request construction, retry logic with exponential backoff, timeout handling, and error classification | 8 | Abed Al Qader Madi
2.2 | LMS document sync service | Implement poll or webhook handler for LMS document publish and update events, download file to local storage, trigger document indexing pipeline on receipt | 10 | Abed Al Qader Madi
2.3 | Institutional data sync service | Consume PSUT academic API or ingest structured data dump to sync courses, course sections, student enrolments, and instructor assignments on configurable semester-start schedule | 10 | Yehya Mujahid
2.4 | APScheduler integration | Configure APScheduler for document sync, institutional data sync, notification aggregation, and semester-start trigger jobs. Implement job monitoring and failure alerting | 4 | Mohammad Abzakh
2.5 | Data access and API credential provisioning | Receive, securely store, and validate all required credentials and API keys from PSUT , LMS API, academic data system, student portal , and verify connectivity to each | 4 | Lina Khalil
2.6 | Document ingestion pipeline | Implement file type detection, text extraction for PDF, DOCX, PPTX, and TXT formats, language detection, semantic chunking with configurable chunk size and overlap strategy | 8 | Mahmoud Qaddoura
2.7 | Embedding pipeline | Implement OpenAI text-embedding-3-small client with batch embedding support, upsert vectors to Qdrant with full metadata payload , document ID, chunk ID, course ID, semester, filename, hash | 8 | Mahmoud Qaddoura
2.8 | RAG retrieval service | Implement vector similarity search on Qdrant with course and semester metadata filters, top-k chunk retrieval, overlapping chunk deduplication, and relevance scoring | 10 | Abed Al Qader Madi
2.9 | Prompt and context assembly service | Implement system prompt builder, context window assembly from retrieved chunks, chat history injection, query normalisation, and token budget management | 8 | Mahmoud Qaddoura
2.10 | OpenAI GPT-4.1 streaming client | Implement async OpenAI client with streaming response support, SSE chunk wrapper, rate limit handling with retry, token usage tracking, and error classification | 8 | Yehya Mujahid
2.11 | Chat session management | Implement chat session creation, retrieval, and course-scoped session isolation. Handle session expiry, orphaned session cleanup, and concurrent session limits per user | 8 | Yehya Mujahid
2.12 | Chat API endpoint | Implement POST /chat with StreamingResponse, authentication and enrolment guard, session management integration, full RAG pipeline invocation, and SSE response streaming | 4 | Mohammad Abzakh
2.13 | Chat history persistence | Persist user and assistant turns to ChatMessage table after each exchange, retrieve bounded history window for context injection, implement history pruning strategy | 4 | Mohammad Abzakh
2.14 | Unanswered question detection | Implement heuristic and retrieval confidence-based detection for queries the knowledge base cannot answer, flag and persist unanswered queries with course and user context | 8 | Abed Al Qader Madi
2.15 | Unanswered question notification service | Aggregate flagged unanswered questions per course, generate lecturer in-platform notification with question list, persist notification records with read and dismiss state | 8 | Yehya Mujahid
2.16 | Smart notification service | Implement student notification on new material availability and lecturer notification when student engagement drops below configurable threshold. Support notification preferences per user | 10 | Abed Al Qader Madi
2.17 | Quiz generation service | Implement past paper upload handler, text extraction, quiz generation prompt construction, GPT-4.1 invocation, structured quiz output parsing and persistence with course and paper linkage | 8 | Yehya Mujahid
2.18 | Quiz API endpoints | Implement POST /quizzes for past paper upload and quiz generation, GET /quizzes/{course_id} for quiz retrieval, authentication and lecturer-only upload guard | 8 | Yehya Mujahid
2.19 | Performance report generation service | Aggregate student interaction data per course, construct report prompt with retrieved context, invoke GPT-4.1, parse structured report output, persist with course and lecturer linkage | 8 | Mahmoud Qaddoura
2.20 | Performance report API endpoints | Implement POST /reports/generate for report creation, GET /reports/{id} for retrieval, authentication and lecturer-only access guard, report status polling endpoint | 6 | Mohammad Abzakh
2.21 | Audit logging middleware | Implement request interceptor writing audit record to AuditAI table for every AI response , query text, model output, documents accessed, token usage, latency, timestamp | 6 | Mohammad Abzakh
2.22 | Document usage tracking | Increment per-document usage counters and update last-used timestamp on every retrieval event. Expose aggregated usage statistics per course | 4 | Abed Al Qader Madi
2.23 | Analytics API endpoints | Implement GET /analytics/engagement, /analytics/document-usage, /analytics/unanswered-questions with lecturer and admin role scoping and semester filtering | 8 | Mohammad Abzakh
2.24 | Frontend integration and API contract alignment | Audit existing frontend API calls against new backend contracts, update request structures and response handlers, resolve breaking changes, verify all existing UI flows against new backend | 8 | Lina Khalil
2.25 | QA - unit tests for AI Tutor repositories | Write Pytest unit tests for all AI Tutor repository CRUD operations , chat sessions, messages, documents, audit records , against isolated test database | 2 | Mahmoud Qaddoura
2.26 | QA - unit tests for AI Tutor services | Write Pytest unit tests for chat service, document ingestion, embedding pipeline, RAG retrieval, notification service, quiz generation, and report generation with mocked external dependencies | 2 | Mahmoud Qaddoura
2.27 | QA - integration tests for AI Tutor | Write and execute end-to-end integration tests for AI Tutor against staging environment with live LMS and academic data integrations, validate all API endpoints and data flows | 2 | Mahmoud Qaddoura
2.28 | Documentation - AI Tutor API reference | Write complete API reference documentation for all AI Tutor endpoints , request and response schemas, authentication requirements, error codes, and usage examples. Generated via FastAPI auto-docs and supplemented with narrative documentation. | 6 | Mohammad Abzakh
2.29 | Documentation - RAG pipeline and knowledge base | Document the RAG pipeline , document ingestion flow, chunking strategy, embedding model, Qdrant collection structure, retrieval logic, and prompt assembly. Includes configuration parameters and tuning guidance. | 6 | Mahmoud Qaddoura
2.30 | Documentation - QA test plan and test results - AI Tutor | Document test plan covering scope, test cases, pass/fail criteria, and environment setup. Append test execution results and any defects raised during AI Tutor testing. | 4 | Mahmoud Qaddoura
Estimated Effort in Accumulated Work Days: 244 ¦ Total Business days: 50
Milestone 3 - Academic Advisor Core · Weeks 16-26
3.1 | Academic data ingestion module - abstraction layer | Implement abstract ingestion interface with common output schema supporting three interchangeable input methods , data dump, direct DB read, REST API , without requiring changes to downstream components | 6 | Abed Al Qader Madi
3.2 | Data dump parser | Implement parser for structured CSV or SQL dump of student academic records , completed courses, grades, GPA, credit hours, study plan, enrolment year, expected graduation , with validation and error reporting | 6 | Abed Al Qader Madi
3.3 | Direct database read adapter | Implement read-only SQLAlchemy connection to PSUT academic database, query student records across relevant tables, map to internal schema with field validation | 8 | Yehya Mujahid
3.4 | PSUT academic API adapter | Implement HTTP client for PSUT student data API with paginated fetch, response mapping to internal schema, error handling, and rate limit compliance | 8 | Yehya Mujahid
3.5 | Student survey ingestion | Consume end-of-semester student survey responses from PSUT portal API or structured export, validate response completeness, and persist per student per semester with linkage to academic record | 6 | Abed Al Qader Madi
3.6 | Report job queue - table and worker base | Create ReportJob table with status state machine , pending, in_progress, completed, failed, dead_letter. Implement SELECT FOR UPDATE SKIP LOCKED job claiming and worker base class with status transition methods | 8 | Yehya Mujahid
3.7 | Parallel batch worker | Implement two concurrent worker processes each independently claiming and processing jobs from the queue. Support configurable concurrency level and graceful shutdown on signal | 8 | Abed Al Qader Madi
3.8 | Retry logic and dead letter handling | Implement per-job retry counter with configurable maximum, exponential backoff between attempts, permanent failure promotion to dead letter log with error detail, and admin-accessible dead letter endpoint | 6 | Yehya Mujahid
3.9 | Watchdog mechanism | Implement background coroutine that periodically scans for jobs stuck in in_progress state beyond configurable timeout, requeues stalled jobs, and logs recovery events | 6 | Abed Al Qader Madi
3.10 | Semester-end cron trigger | Implement APScheduler job firing at configured semester-end date to enqueue all active students into the report job queue, with duplicate prevention and run logging | 6 | Mohammad Abzakh
3.11 | Batch monitoring endpoints | Implement GET /advisor/jobs/status returning batch run progress , total, pending, in_progress, completed, failed counts , and GET /advisor/jobs/dead-letter listing permanently failed jobs with error details | 6 | Mohammad Abzakh
3.12 | Ollama client for local model | Implement async Ollama HTTP client with request construction, streaming response handling, timeout management, error classification, and multi-instance round-robin load distribution | 8 | Yehya Mujahid
3.13 | Report generation prompt engineering | Design, iterate, and validate system and user prompt templates for course recommendations, elective guidance, and career path sections. Test across diverse student profile scenarios with academic record and survey context inputs | 10 | Mahmoud Qaddoura
3.14 | Structured output parsing and validation | Implement parser for LLM JSON output into typed report schema , course recommendations list, elective guidance list, career path section. Validate completeness, handle malformed output, trigger retry on parse failure | 8 | Abed Al Qader Madi
3.15 | Report JSONB storage | Persist structured report data to AcademicReport table with student ID, semester, generation timestamp, model version, and generation metadata. Implement idempotent upsert for re-generation scenarios | 6 | Yehya Mujahid
3.16 | PDF rendering pipeline | Merge structured report data with PSUT official PDF template using WeasyPrint or ReportLab. Stream rendered PDF on demand. Support template version management for future template updates | 10 | Mohammad Abzakh
3.17 | Report retrieval API endpoint | Implement GET /advisor/report/{student_id}/{semester} , validate portal authentication token, fetch structured report from database, render PDF, return as streamed file response | 8 | Mohammad Abzakh
3.18 | Report ready notification | Trigger student notification through PSUT portal API when report generation completes successfully. Include fallback for portal API unavailability with retry queue | 6 | Yehya Mujahid
3.19 | Synthetic training data pipeline | Implement script to generate diverse synthetic student academic profiles covering strong performers, at-risk students, mixed performance, various years and programmes. Generate paired advisory report outputs using GPT-4.1. Export as JSONL training dataset | 8 | Mahmoud Qaddoura
3.20 | LoRA fine-tuning script | Configure and execute LoRA fine-tuning on selected base model using Hugging Face PEFT library. Implement training loop with checkpoint saving, evaluation metric logging, and export of fine-tuned weights for production deployment | 10 | Abed Al Qader Madi
3.21 | Model validation and deployment packaging | Validate fine-tuned model against held-out test profiles, compare output quality against base model baseline, package model weights for transfer to production GPU server | 6 | Mahmoud Qaddoura
3.22 | QA - unit tests for Academic Advisor components | Write Pytest unit tests for data ingestion module, batch worker job claiming and state transitions, watchdog mechanism, prompt builder, structured output parser, and PDF renderer | 6 | Mahmoud Qaddoura
3.23 | QA - integration tests for Academic Advisor | Execute full pilot batch generation against representative synthetic student dataset in staging environment. Validate report structure, content quality, generation throughput, retry behaviour, and dead letter handling | 6 | Mahmoud Qaddoura
3.24 | QA - portal integration testing | Test report retrieval API end-to-end with PSUT student portal team in staging environment. Validate authentication, PDF rendering, response times, and error handling for edge cases | 6 | Mahmoud Qaddoura
3.25 | Documentation - Academic Advisor API reference | Write complete API reference for all Academic Advisor endpoints , report retrieval, job status, dead letter , including authentication requirements, response schemas, error codes, and integration guidance for the PSUT portal team | 6 | Mohammad Abzakh
3.26 | Documentation - batch processing and fine-tuning guide | Document the batch report generation architecture, job queue design, cron trigger configuration, retry logic, and watchdog behaviour. Include fine-tuning pipeline steps, dataset preparation, training configuration, and model deployment process | 4 | Mahmoud Qaddoura
3.27 | Documentation - QA test plan and test results - Academic Advisor | Document test plan for Academic Advisor covering batch generation, portal integration, and report quality validation. Append test execution results, defect log, and sign-off checklist | 4 | Mahmoud Qaddoura
Estimated Effort in Accumulated Work Days: 226 ¦ Total Business days: 50
Milestone 4 - Integration, Testing & Deployment · Weeks 26-34
4.1 | Load testing - AI Tutor | Simulate concurrent student and lecturer traffic on AI Tutor using Locust or k6. Test chat endpoint under peak exam-period load, measure response latency, error rate, and throughput at defined concurrency levels | 8 | Lina Khalil
4.2 | Load testing - Academic Advisor batch | Benchmark full 5,000-student batch generation run in staging environment. Measure per-report generation time, worker throughput, queue drain rate, and GPU utilisation across the batch window | 8 | Lina Khalil
4.3 | Performance bottleneck resolution | Analyse load test results, identify bottlenecks in database queries, API response times, or inference throughput, implement targeted optimisations, and retest to verify improvement | 10 | Mahmoud Qaddoura
4.4 | Security testing - authentication and authorisation | Test JWT token validation, token expiry enforcement, role-based access control boundaries, course-scoped enrolment checks, and unauthorised access rejection across all endpoints | 6 | Mohammad Al Balawi
4.5 | Security testing - data isolation and injection | Test cross-user and cross-course data isolation, SQL injection resistance across all database query paths, prompt injection resistance in AI endpoints, and API key exposure in logs and responses | 6 | Mohammad Al Balawi
4.6 | Security testing - infrastructure and network | Test production server hardening , open port exposure, SSL/TLS configuration, HTTP security headers, secrets management, environment variable exposure, and Docker container isolation | 6 | Mohammad Al Balawi
4.7 | Security findings remediation | Review all security test findings, prioritise by severity, implement fixes for all critical and high findings, retest remediated items to confirm resolution | 8 | Mohammad Abzakh
4.8 | Production environment configuration | Configure production server , environment variables, secrets management via vault or encrypted env files, Nginx reverse proxy with SSL termination, firewall rules, and service startup scripts | 8 | Lina Khalil
4.9 | Academic Advisor GPU server setup | Configure PSUT on-premises GPU server , install CUDA toolkit, Ollama, deploy fine-tuned model weights, configure parallel inference instances, verify batch worker connectivity and job processing | 6 | Mohammad Al Balawi
4.10 | Staged production deployment - AI Tutor | Deploy AI Tutor to production in staged rollout , deploy backend first, run smoke tests, enable for limited user group, monitor error rates and latency, proceed to full rollout on confirmation | 4 | Lina Khalil
4.11 | Staged production deployment - Academic Advisor | Deploy Academic Advisor API and batch worker to production GPU server, verify database connectivity and job queue operation, run pilot batch on small student subset, confirm PDF generation and portal delivery | 4 | Lina Khalil
4.12 | Monitoring and observability setup | Configure Prometheus metrics collection and Grafana dashboards for both subsystems , API latency, error rates, request throughput, GPU utilisation, inference latency, batch job progress, and storage usage | 4 | Mohammad Al Balawi
4.13 | UAT coordination with PSUT stakeholders | Coordinate user acceptance testing with PSUT representatives , eLearning team, lecturers, student portal team. Manage UAT schedule, collect structured feedback, log issues, and obtain written UAT sign-off | 10 | Yazan Abu Osbeh
4.14 | Go-live stakeholder communication | Prepare and distribute go-live communication to PSUT stakeholders , announcement of platform availability, user guidance, support contact information, and known limitations | 4 | Yazan Abu Osbeh
4.15 | Post-launch monitoring and issue triage | Monitor production systems during initial go-live period, triage and prioritise any reported issues, coordinate hotfix deployment if critical issues arise, and provide daily status updates to PSUT | 4 | Lina Khalil
4.16 | Documentation - deployment and configuration guide | Write comprehensive deployment guide covering production environment setup, environment variable reference, Nginx configuration, SSL setup, service startup and shutdown procedures, and rollback steps | 4 | Mohammad Al Balawi
4.17 | Documentation - system components and operations runbook | Document all system components, their responsibilities, dependencies, and operational procedures , how to restart services, handle common failure scenarios, manage semester transitions, and perform routine maintenance | 6 | Mahmoud Qaddoura
4.18 | Documentation - security controls and compliance | Document all security controls implemented across both subsystems , authentication mechanism, authorisation model, data isolation approach, secrets management, audit logging, and data privacy measures | 8 | Mohammad Al Balawi
4.19 | Documentation - QA and testing summary report | Compile final QA summary report covering all testing phases , unit, integration, load, security, and UAT. Include test coverage metrics, defect summary, resolution status, and overall quality sign-off | 4 | Lina Khalil
4.20 | Documentation - user guide and training materials | Write end-user documentation for lecturers, students, and admins covering platform features, how-to guides for key workflows, FAQ, and troubleshooting. Prepare training material slides for PSUT onboarding session | 8 | Yazan Abu Osbeh
4.21 | Project closure and handover | Prepare project closure report, conduct knowledge transfer session with PSUT IT team, hand over all credentials, documentation, and repository access, and obtain final project sign-off from PSUT | 6 | Yazan Abu Osbeh
Estimated Effort in Accumulated Work Days: 150 ¦ Total Business days: 40

## Legend & Summary
Project Legend & Workload Summary
Colour Legend — Grouped by Role
Milestone 1 — Requirements & Foundation
Milestone 2 — AI Tutor Core
Milestone 3 — Academic Advisor Core
Milestone 4 — Integration, Testing & Deployment
Yazan Abu Osbeh — Project Manager — Stakeholder coordination, project management, UAT, handover
Mahmoud Qaddoura — Lead AI Engineer — Architecture, RAG pipeline, prompt engineering, fine-tuning
Abed Al Qader Madi — AI Engineer — AI development tasks
Yehya Mujahid — AI Full Stack Developer — AI development tasks
Mohammad Abzakh — Full Stack Lead — Backend APIs, frontend
Lina Khalil — Devops and Systems Engineer — deployment, DevOps, monitoring
Mohammad Al Balawi — Dev-Secops and systems Lead — Security and penetration testing, deployment, DevOps, monitoring
Workload Summary of Effort Days and Business Days by Milestone
Milestone | Timeline | Yazan (PM) | Mahmoud (Lead AI) | Abzakh (Fullstack Lead) | Abed (AI Eng) | Yehya (AI Dev) | Lina (Devops) | Balawi (Security & Devops lead)
Milestone 1 — Requirements & Foundation | Weeks 1–6 (30 B.D) | 30 | 30 | 12 | 14 | 14 | 6 | 8
Milestone 2 — AI Tutor Core | Weeks 6–16 (50 B.D) | 0 | 48 | 38 | 50 | 50 | 12 | 0
Milestone 3 — Academic Advisor Core | Weeks 16–26 (50 B.D) | 0 | 50 | 36 | 50 | 50 | 0 | 0
Milestone 4 — Integration, Testing & Deployment | Weeks 26–34 (40 B.D) | 28 | 16 | 8 | 0 | 0 | 40 | 40
TOTAL Effort | ~34 Weeks / 8 Months | 58 | 144 | 94 | 114 | 114 | 58 | 48
Hourly Rate | JoD/Hour | 8 | 6 | 6 | 4 | 4 | 4 | 6
TOTAL Reimbursement Rounded | Total Cost = Total Days × 8 × Hourly Rate × 1.20 | 4454.4 | 8294.4 | 5414.4 | 4377.6 | 4377.6 | 2227.2 | 2764.8